## Sheet1
	Project name : Job Portal
	Scrum : Sprint -1 (Project Baseline)
1	Database wire frame preparation	04.05.19
2	Database script preparation	06.05.19
3	Database review /execution	07.05.19
4	Abstract document preparation	07.05.19
5	Project baseline-setup	07.05.19
6	Project maven integration	07.05.19
7	Project identify the business logic	07.05.19
8	Project display menu items	07.05.19
9	Adding common modules(Login,Payment,Utilities	08.05.19
10	Project-validation implementation	08.05.19
11	Project -DAO implementation	08.05.19
12	Servlet /Implementation controller	09.05.19
13	Service/Business implementation	09.05.19
14	Feature wise -DAO implementation	10.05.19
15	Utilities-common Functionality implementation	10.05.19
16	JavaScript Session part 1	14-05-2019
17	Project Updates, Agile Introduction	14-05-2019
18	Project Demo	14-05-2019
19	one to one Discussions	14-05-2019
20	SQL Batch Update- Sample	15-05-2019
21	Junit Session	15-05-2019
22	Log4j session	15-05-2019
23	Utilities – External Utility API (String Utils, File Utils)	16-05-2019
24	Convert Dynamic web -> Maven Project	16-05-2019
25	JavaScript (Page redirect, Dialog boxes, HTML DOM, Validations) (Part-2)	17-05-2019
26	One to one Questions	17-05-2019
27	Project Demo – 2nd Review	17-05-2019
28	Assessment- L2 & L3	17-05-2019
29	Scenario based Questions (discussion)	17-05-2019
30	Jquery/Js Ajax (diff)	20-05-2019
31	JDBC/GC/Arrays	20-05-2019
32	Web Application Configuration	20-05-2019
33	Abstract document - Reviewed	21-05-2019
34	Demo Project Review	21-05-2019
35	Naming convention / coding standards	21-05-2019
36	defined exceptions / joins / sub query	21-05-2019
37	UI – validations / alignments / css	21-05-2019
38	Final Project review	21-05-2019
39	Demo to client	24-05-2019
40	share source code / DB scipts – git repository	24-05-2019